|  |  |  |  |  |  |  |  |  |  |  |  |  | Data Collection |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Data Cleaning & Vicualization |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Update Report |  |  |  |  |  |  |  |  |  |
| Project Title: 2025 Bioindicators Report |  |  |  |  |  |  |  |  |  |  |  |  | Due Dates |  |  |  |  |  |  |  |  |  |
| PHASES Phase 1. Data Collection | Tasks | Responsible Party | Deliverables/Outputs | Due Dates |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | 8-15-Sep | 22-Se p | 29-Sep | 6-Oct | 13-Oct | 20-Oct | 27-Oct | 3-Nov | 10-Nov |  | 17-Nov | 24-Nov | 1-Dec | 8-Dec | 11-Dec |  |  | 15-Jan 22-Jan | 29-Jan |
| Ethanol | 1 | Blythe | Collect 2024 data for Ethanol |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Biobutanol |  | Blythe | Collect 2024 data for Biobutanol |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Biodiesel | 1 | Blythe | Collect 2024 data for Biodiesel |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Renewable Diesel | 2 | Blythe | Collect 2024 data for Renewable Diesel |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Agricultural Summary |  | Blythe | Collect 2024 data for Agricultural Summary |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Barley | 1 | Blythe | Collect 2024 data for Barley |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Wheat | 2 | Blythe | Collect 2024 data for Wheat |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Corn | 3 | Blythe | Collect 2024 data for Corn |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Renewable Jet Fuel |  | Donough | Collect 2024 data for Renewable Jet Fuel |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Wood Pellets | 1 | Donough | Collect 2024 data for Wood pellets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Waste to Energy | 2 | Donough | Collect 2024 data for Waste to Energy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Biogas | 3 | Donough | Collect 2024 data for Biogas |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Trade | 4 | Donough | Collect 2024 data for Trade |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CSC |  | Donough | Collect 2024 data for CSC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sroghum | 1 | Donough | Collect 2024 data for Sorghum |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Soy Data | 2 | Donough | Collect 2024 data for Soy Data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cotton | 3 | Donough | Collect 2024 data for Cotton |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Bioproducts | 4 | Rebecca | Collect 2024 data for Bioproducts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Bioplastics | 5 | Rebecca | Collect 2024 data for Bioplastics |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Enzymes | 6 | Rebecca | Collect 2024 data for Enzymes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Forest Products | 7 | Rebecca | Collect 2024 data for Forest Products |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Apparel & Textiles | 8 | Rebecca | Collect 2024 data for Apparel & Textiles |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Funding | 9 | Rebecca | Collect 2024 data for Funding |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Peanuts | 10 | Rebecca | Collect 2024 data for Peanuts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sunflowers |  | Rebecca | Collect 2024 data for Sunflowers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Canola | 1 | Rebecca | Collect 2024 data for Canola |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase 2: Data Cleaning & Visualization | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ethanol | 3 | Blythe | Create visualization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Biobutanol | 4 | Blythe | Create visualization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Biodiesel | 5 | Blythe | Create visualization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Renewable Diesel |  | Blythe | Create visualization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Agricultural Summary | 1 | Blythe | Create visualization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Barley | 2 | Blythe | Create visualization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Wheat | 3 | Blythe | Create visualization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Corn |  | Blythe | Create visualization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Renewable Jet Fuel | 1 | Donough | Create visualization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Wood Pellets | 2 | Donough | Create visualization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Waste to Energy | 3 | Donough | Create visualization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Biogas | 4 | Donough | Create visualization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Trade |  | Donough | Create visualization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CSC | 1 | Donough | Create visualization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sroghum | 2 | Donough | Create visualization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Soy Data | 3 | Donough | Create visualization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cotton | 4 | Donough | Create visualization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Bioproducts |  | Rebecca | Create visualization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Bioplastics | 1 | Rebecca | Create visualization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Enzymes | 2 | Rebecca | Create visualization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Forest Products | 3 | Rebecca | Create visualization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Apparel & Textiles |  | Rebecca | Create visualization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Funding | 1 | Rebecca | Create visualization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | tbd |
| Peanuts | 2 | Rebecca | Create visualization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | tbd |
| Sunflowers | 3 | Rebecca | Create visualization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | tbd |
| Canola |  | Rebecca | Create visualization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase 3: Update Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Ethanol | 1 | Blythe | Populate Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Biobutanol |  | Blythe | Populate Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Biodiesel | 1 | Blythe | Populate Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Renewable Diesel | 2 | Blythe | Populate Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Agricultural Summary |  | Blythe | Populate Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Barley | 1 | Blythe | Populate Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Wheat | 2 | Blythe | Populate Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Corn | 3 | Blythe | Populate Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Renewable Jet Fuel |  | Donough | Populate Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Wood Pellets | 1 | Donough | Populate Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Waste to Energy | 2 | Donough | Populate Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Biogas | 3 | Donough | Populate Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Trade | 4 | Donough | Populate Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CSC |  | Donough | Populate Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sroghum | 1 | Donough | Populate Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Soy Data | 2 | Donough | Populate Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cotton | 3 | Donough | Populate Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Bioproducts | 4 | Rebecca | Populate Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Bioplastics | 5 | Rebecca | Populate Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Enzymes | 6 | Rebecca | Populate Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Forest Products | 7 | Rebecca | Populate Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Apparel & Textiles | 8 | Rebecca | Populate Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Funding | 9 | Rebecca | Populate Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Peanuts | 10 | Rebecca | Populate Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sunflowers |  | Rebecca | Populate Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Canola | 1 | Rebecca |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |